## Timeline
SN | Milestone | Step | Main Task | Sub Task | Details | Faclon | Adani Cement | AWS | Start Date | Target Date | Revised Target Date | Actual Start Date | Actual End Date | Status | Faclon Remarks for Delay | Remarks | Handoffs to Adani
1 | M1 | Project Initiation | Project Initiation | PoC Kick-Off & Scope Freeze | > Kick-off with Adani Cement, Faclon and AWS teams > Freeze scope against both SOWs dated 10 Aug 2026 - Golden Operating Window for Rotary Kiln, and Soft Sensor for Clinker C3S & Free Lime Prediction > Agree review cadence, escalation path and single point of contact per team | TRUE | TRUE | TRUE | 2026-08-28 | 2026-08-28 |  |  |  | Not Started |  |  | PoC scope document and RACI
|  |  |  | Tag List & Parameter Mapping | > Share DCS / historian tag list for kiln, preheater, calciner, cooler and fuel systems > Map tags to process parameters and engineering units > Identify lab sampling points, frequency and test method for all quality parameters | TRUE | TRUE | FALSE | 2026-08-28 | 2026-09-04 |  |  |  | Not Started |  | Dependency: 1. Adani Cement - tag list with descriptions and engineering units | Verified tag-to-parameter mapping sheet
|  |  |  | KPI, Target & Control Limit Definition | > Confirm the KPI set - Clinker Production, Specific Heat Consumption (SHC), Thermal Substitution Rate (TSR) and Clinker Quality > Adani quality team to provide target values, USL and LSL for C3S and Free Lime > Agree the productivity levels at which control limits are to be derived | TRUE | TRUE | FALSE | 2026-08-28 | 2026-09-04 |  |  |  | Not Started |  | Dependency: 1. Adani Cement quality team to provide C3S and Free Lime target, USL and LSL (SOW Soft Sensor - Notes & Assumptions) | Agreed KPI set with targets, USL and LSL
|  | GOW - Historical Data Assessment | Historical Data Assessment | Historical Process Data Validation - Kiln Circuit | > Validate the minimum 12 months of historical process data received on 28 Aug 2026 > Review data availability across the kiln, preheater, calciner, cooler and fuel systems > Profile missing values, frozen tags, outliers and sensor drift per tag | TRUE | TRUE | FALSE | 2026-08-28 | 2026-09-08 |  |  |  | Not Started |  |  | Kiln circuit data availability and quality report
|  |  |  | Historical Quality & Laboratory Data Validation | > Validate 12 months of laboratory quality data against the same process data period > Review clinker quality, SHC, TSR and clinker production records > Flag manual-entry and transcription gaps in the laboratory records | TRUE | TRUE | FALSE | 2026-08-28 | 2026-09-08 |  |  |  | Not Started |  |  | Quality data availability and quality report
|  | Soft Sensor - Historical Data Assessment | Historical Data Assessment | Process, Fuel & Raw Meal Chemistry Data Validation | > Review data availability across kiln process parameters and quality control data > Cover kiln feed, clinker, hotmeal chemistry and degree of calcination > Cover fuel mix including fossil fuel and AFR | TRUE | TRUE | FALSE | 2026-08-28 | 2026-09-08 |  |  |  | Not Started |  |  | Soft sensor input data availability report
|  |  |  | Lab Sampling Alignment for C3S & Free Lime | > Align continuous process data with discrete C3S and Free Lime lab sample timestamps > Establish material residence time between the kiln and the sampling point > Assess feasibility of quality data interpolation to support 15-30 minute prediction | TRUE | TRUE | FALSE | 2026-09-09 | 2026-09-15 |  |  |  | Not Started |  |  | Time-aligned C3S and Free Lime modelling dataset
|  | Data Readiness | Data Preparation & Sign-Off | Historical Data Cleaning - Shutdowns, Start-Ups & Abnormal Periods | > Clean and prepare the historical operating data for both use cases > Remove shutdowns, start-ups and abnormal operating periods > Adani process experts to validate the excluded periods | TRUE | TRUE | FALSE | 2026-09-09 | 2026-09-15 |  |  |  | Not Started |  |  | Cleaned 12-month historical dataset with exclusion log
|  |  |  | Baseline Dataset Freeze & Data Readiness Sign-Off | > Freeze the training and validation datasets for both workstreams > Joint sign-off that the data is fit for model development > Record known data limitations carried into the PoC | TRUE | TRUE | FALSE | 2026-09-16 | 2026-09-17 |  |  |  | Not Started |  |  | Data readiness sign-off
2 | M2 | GOW - Window Development | Golden Operating Window Development | Best-Performing Period Identification | > Identify historically best-performing operating periods from the cleaned 12-month dataset > Rank periods on productivity, SHC, TSR and clinker quality > Segment the identified periods by productivity level | TRUE | FALSE | FALSE | 2026-09-18 | 2026-10-02 |  |  |  | Not Started |  |  | Historical benchmark of best-performing operating periods
|  |  |  | Control Limit Derivation at Different Productivity Levels | > Derive recommended operating control limit ranges for all agreed key kiln process and quality parameters > Produce a distinct set of control limits for each agreed productivity level > Assemble the plant-specific Golden Batch of control limits | TRUE | FALSE | FALSE | 2026-09-25 | 2026-10-16 |  |  |  | Not Started |  |  | SOW Deliverable A - Golden Operating Window, Golden Batch Optimum Control Limits
|  |  |  | Joint Validation with Plant Process Experts & Faclon SME | > Review the derived control limit ranges with the plant operations team and Adani process experts > Faclon SME validation of the window against kiln process behaviour > Freeze the validated Golden Operating Window for shadow testing | TRUE | TRUE | FALSE | 2026-10-12 | 2026-10-23 |  |  |  | Not Started |  |  | Jointly validated Golden Operating Window
|  | Soft Sensor - Model Development | Soft Sensor Model Development | ML Model Development - Clinker C3S Prediction | > Develop machine learning model to predict clinker C3S from process and quality parameters > Train on the frozen 12-month dataset using kiln feed, hotmeal chemistry, degree of calcination and fuel mix > Build towards prediction at 15-30 minute frequency | TRUE | FALSE | FALSE | 2026-09-18 | 2026-10-13 |  |  |  | Not Started |  |  | C3S prediction model
|  |  |  | ML Model Development - Clinker Free Lime Prediction | > Develop machine learning model to predict clinker Free Lime from process and quality parameters > Train on the frozen 12-month dataset using kiln thermal profile, fuel mix and AFR > Build towards prediction at 15-30 minute frequency | TRUE | FALSE | FALSE | 2026-09-18 | 2026-10-13 |  |  |  | Not Started |  |  | Free Lime prediction model
|  |  |  | Prediction Frequency Finalisation (15 / 30 minutes) | > Finalise the prediction frequency jointly, based on data availability and business requirement > Confirm the interpolation approach for quality data between laboratory samples | TRUE | TRUE | FALSE | 2026-10-05 | 2026-10-13 |  |  |  | Not Started |  | Dependency: 1. SOW Soft Sensor - Notes & Assumptions. Frequency to be finalised jointly during implementation. | Agreed prediction frequency and interpolation approach
|  |  |  | Model Validation Against Historical Laboratory Results | > Validate model performance on a hold-out period against actual laboratory results > Report accuracy per model in absolute terms and on trend > Document failure modes and operating regimes with weak data coverage | TRUE | FALSE | FALSE | 2026-10-12 | 2026-10-23 |  |  |  | Not Started |  |  | SOW Deliverable A - Soft Sensor Model with historical validation results
|  | RCA & Recommendations Development | Root Cause Analysis Engine | RCA Model Development - Kiln KPIs | > Develop root cause analysis for selected critical KPIs on deviation from the Golden Operating Window > Cover SHC, TSR, SAT, TAT and BZT as the initial critical KPI set > Expandable to further KPIs in later phases per SOW note | TRUE | FALSE | FALSE | 2026-09-28 | 2026-10-20 |  |  |  | Not Started |  |  | RCA engine for kiln KPIs
|  |  |  | RCA Model Development - Clinker Quality Deviations | > Develop RCA guidance for C3S and FcaO deviations from their target values > Attribute deviations to the corresponding kiln operating conditions | TRUE | FALSE | FALSE | 2026-09-28 | 2026-10-20 |  |  |  | Not Started |  |  | RCA engine for clinker quality deviations
|  |  | Operator Recommendation Engine | Prioritised Recommendation Logic | > Generate prioritised, operator-friendly recommendations to restore operation towards the Golden Operating Window control limits > Generate recommendations to recover clinker quality within the desired operating limits > Prioritisation to follow the operator-defined priorities agreed with the plant team | TRUE | TRUE | FALSE | 2026-10-05 | 2026-10-23 |  |  |  | Not Started |  |  | SOW Deliverable C - Root Cause Analysis & Recommendations
|  |  |  | Advisory Framing & Joint Review Protocol | > Confirm all outputs are presented as advisory, to support operator decision-making > Agree the joint review protocol with plant operations, Adani process experts and Faclon SMEs > Plant team retains responsibility for operational decisions and execution | TRUE | TRUE | FALSE | 2026-10-19 | 2026-10-23 |  |  |  | Not Started |  | Per Notes & Assumptions in both SOWs - recommendations are advisory. Operational changes to be implemented by the plant team after appropriate technical verification. | Agreed advisory and joint review protocol
|  | Live Data Integration | Live Data Pipeline Setup | Live Data Interface Design & Agreement | > Agree push mechanism, schema, frequency and latency for real-time process and quality data > Confirm the feed meets the frequency required for 15-30 minute prediction > No hardware in scope - software integration only | TRUE | TRUE | TRUE | 2026-09-18 | 2026-09-25 |  |  |  | Not Started |  |  | Live data interface specification
|  |  |  | Real-Time Data Feed Setup by Adani / AWS | > Adani Cement and AWS to make real-time process and quality data available at the required frequency > Provision credentials, endpoints and network access > Confirm live tag coverage matches the 12-month historical dataset | FALSE | TRUE | TRUE | 2026-09-28 | 2026-10-16 |  |  |  | Not Started |  | Dependency: 1. Owned by Adani Cement and AWS, per the Notes in both SOWs 2. Shadow testing cannot start until this feed is live and stable
|  |  |  | Live Feed Ingestion & Validation at Faclon | > Ingest the real-time feed onto IOsense and validate against DCS / HMI values > Check timestamp alignment, engineering units and update frequency > Confirm feed stability over a continuous run | TRUE | TRUE | TRUE | 2026-10-12 | 2026-10-23 |  |  |  | Not Started |  |  | Validated real-time data feed on IOsense
|  | Application Development | Dashboard Build | Live Benchmarking Dashboard Build | > Real-time comparison of live operation against the Golden Operating Window at different productivity levels > Parameter-wise deviation monitoring > Overall Golden Window compliance view | TRUE | FALSE | FALSE | 2026-09-28 | 2026-10-23 |  |  |  | Not Started |  |  | SOW Deliverable B - Live Benchmarking Dashboard
|  |  |  | Continuous AI-Driven Monitoring Build | > Real-time display of predicted C3S and Free Lime > Predicted vs actual trend comparison, in absolute terms and on trend > Continuous reconciliation of predicted values against laboratory measurements | TRUE | FALSE | FALSE | 2026-09-28 | 2026-10-23 |  |  |  | Not Started |  |  | SOW Deliverable B - Continuous AI-Driven Monitoring
|  |  |  | RCA & Recommendation Operator Views | > Operator view for root cause analysis output on flagged deviations > Prioritised recommendation display within the operator workflow | TRUE | FALSE | FALSE | 2026-10-12 | 2026-10-23 |  |  |  | Not Started |  |  | RCA and recommendation operator views
|  |  |  | Model - Application Integration & User Walkthrough | > Wire all models and the RCA engine into the application for scheduled inference > Demonstrate to plant, process, CCR and quality users on replayed data > Capture change requests before shadow go-live | TRUE | TRUE | FALSE | 2026-10-19 | 2026-10-23 |  |  |  | Not Started |  |  | Application walkthrough and change request log
3 | M3 | GOW - Online Benchmarking | Shadow Run - Golden Operating Window | Shadow Mode Go-Live | > Golden Operating Window and both soft sensor models switched to the live data feed > All outputs advisory only - no control action > Start of the four-week shadow window | TRUE | TRUE | TRUE | 2026-10-26 | 2026-10-26 |  |  |  | Not Started |  |  | Models running live in shadow mode
|  |  |  | Live Deviation Detection & Window Compliance Tracking | > Continuously compare live operating conditions against the Golden Operating Window > Detect and highlight deviations from the recommended operating ranges > Track overall Golden Window compliance across the shadow period | TRUE | TRUE | FALSE | 2026-10-26 | 2026-11-20 |  |  |  | Not Started |  |  | Weekly Golden Window compliance log
|  |  |  | RCA Output Review with Control Room | > Review RCA output on flagged SHC, TSR, SAT, TAT and BZT deviations with the CCR team > Record operator response and the usefulness of the recommendations | TRUE | TRUE | FALSE | 2026-10-26 | 2026-11-20 |  |  |  | Not Started |  |  | RCA output review log
|  | Soft Sensor - Online Prediction | Shadow Run - Soft Sensor | Live C3S & Free Lime Prediction at Agreed Frequency | > Generate predicted C3S and Free Lime values at the agreed 15-30 minute frequency > Track predicted and actual values in absolute terms as well as on trend > RCA guidance for C3S and Free Lime deviations, based on the corresponding kiln operating conditions | TRUE | TRUE | FALSE | 2026-10-26 | 2026-11-20 |  |  |  | Not Started |  |  | Live prediction log
|  |  |  | Continuous Reconciliation Against Laboratory Measurements | > Reconcile every prediction against the corresponding laboratory measurement > Monitor running prediction accuracy across the shadow window > Feed reconciliation findings back into model improvement | TRUE | TRUE | FALSE | 2026-10-26 | 2026-11-20 |  |  |  | Not Started |  |  | Prediction vs laboratory reconciliation report
|  | Model Tuning & Review | Tuning & Checkpoints | Model Drift Monitoring & In-Flight Tuning | > Monitor drift between offline and live performance for all models > Retune models and control limits against observed live behaviour > Version and document every model change made during shadow | TRUE | FALSE | FALSE | 2026-10-26 | 2026-11-20 |  |  |  | Not Started
|  |  |  | Shadow Review - Checkpoint 1 | > Two-week checkpoint on live accuracy, window compliance and operator feedback > Joint review with plant operations, Adani process experts and Faclon SMEs > Agree corrective actions for the remaining shadow period | TRUE | TRUE | FALSE | 2026-11-09 | 2026-11-09 |  |  |  | Not Started |  |  | Checkpoint 1 review record
|  |  |  | Shadow Review - Checkpoint 2 | > Closing review of the shadow window > Freeze model versions and control limits for PoC evaluation | TRUE | TRUE | FALSE | 2026-11-20 | 2026-11-20 |  |  |  | Not Started |  |  | Checkpoint 2 review record and frozen model versions
4 | M4 | PoC Closure | Evaluation & Handover | SOW Deliverable Sign-Off | > Joint sign-off against every named deliverable of both SOWs > GOW - Golden Operating Window control limits, Live Benchmarking Dashboard, RCA & Recommendations > Soft Sensor - Soft Sensor Model, Continuous AI-Driven Monitoring, RCA & operator recommendations | TRUE | TRUE | FALSE | 2026-11-23 | 2026-11-24 |  |  |  | Not Started |  |  | Signed-off SOW deliverable checklist
|  |  |  | PoC Performance Evaluation | > Consolidate offline and shadow results for the Golden Operating Window and both soft sensors > Evaluate against the KPI targets agreed at kick-off > Quantify observed benefit and projected benefit at scale | TRUE | TRUE | FALSE | 2026-11-23 | 2026-11-25 |  |  |  | Not Started |  |  | PoC evaluation summary
|  |  |  | PoC Report Submission | > Submit the PoC report covering approach, results, limitations and lessons > Include the data and integration dependencies observed during the PoC | TRUE | FALSE | FALSE | 2026-11-24 | 2026-11-25 |  |  |  | Not Started |  |  | PoC report
|  |  |  | Go / No-Go Review & Scale-Up Recommendation | > Joint go / no-go decision with Adani Cement and AWS > Recommendation on expanding RCA and recommendations to further KPIs, per the SOW note > Recommendation on scale-up across assets and sites > Closes the 90-day PoC window (Day 1 = 28 Aug 2026) | TRUE | TRUE | TRUE | 2026-11-26 | 2026-11-26 |  |  |  | Not Started |  |  | Go / No-Go decision and scale-up recommendation (SOW Deliverable - Scalable Across Assets and Sites)