## Timeline
SN | Milestone | Step | Main Task | Sub Task | Details | Faclon | Adani Cement | AWS | Start Date | Target Date | Revised Target Date | Actual Start Date | Actual End Date | Status | Faclon Remarks for Delay | Remarks | Handoffs to Adani
1 | M1 | PoC Kickoff & Data Handover | Project Initiation | PoC Kick-Off Meeting | > Kick-off with Adani Cement, Faclon and AWS teams > Freeze PoC scope: Kiln Golden Batch, C3S soft sensor, Free Lime soft sensor > Agree review cadence, escalation path and single point of contact per team | TRUE | TRUE | TRUE | 2026-08-28 | 2026-08-28 |  |  |  | Not Started |  |  | PoC scope document and RACI
|  |  |  | Tag List & Parameter Mapping | > Share DCS / historian tag list for kiln, preheater, cooler and raw mill > Map tags to process parameters and engineering units > Identify lab sampling points and frequency for C3S and Free Lime | TRUE | TRUE | FALSE | 2026-08-28 | 2026-09-04 |  |  |  | Not Started |  | Dependency: 1. Adani Cement - share tag list with descriptions and units | Verified tag-to-parameter mapping sheet
|  |  | Historical Data Handover | Historical Process Data Handover | > Adani Cement to share historical process data for the agreed period > Data period and logging frequency to be confirmed at kick-off > Transfer over the agreed channel (S3 / SFTP / file export) | TRUE | TRUE | TRUE | 2026-08-28 | 2026-09-04 |  |  |  | Not Started |  | Dependency: 1. Adani Cement - confirm historical data period and frequency 2. AWS - confirm transfer channel and access
|  |  |  | Historical Quality & Lab Data Handover | > Adani Cement to share lab / XRD results for C3S and Free Lime for the same period > Include sample timestamps, sampling location and test method > Flag any manual-entry or transcription gaps in the lab records | TRUE | TRUE | FALSE | 2026-08-28 | 2026-09-04 |  |  |  | Not Started |  | Dependency: 1. Lab data must cover the same period as the process data, otherwise the models cannot be supervised
|  | Data Validation & Exploratory Analysis | Data Quality Assessment | Data Completeness & Gap Assessment | > Profile missing values, frozen tags, outliers and sensor drift > Quantify usable data coverage per tag > Raise the consolidated data gap list back to Adani Cement | TRUE | FALSE | FALSE | 2026-09-07 | 2026-09-11 |  |  |  | Not Started |  |  | Data gap and data quality report
|  |  |  | Process - Lab Time Alignment | > Align continuous process data with discrete lab sample timestamps > Establish material residence time / lag between kiln and sampling point > Build the time-aligned modelling dataset | TRUE | TRUE | FALSE | 2026-09-07 | 2026-09-11 |  |  |  | Not Started
|  |  | Exploratory Data Analysis | Feature Engineering & Correlation Analysis | > Derive features from kiln, preheater, cooler, fuel and raw mix parameters > Correlation and sensitivity analysis against C3S and Free Lime > Shortlist driver variables jointly with the Adani process team | TRUE | TRUE | FALSE | 2026-09-08 | 2026-09-16 |  |  |  | Not Started |  |  | EDA findings and shortlisted driver variables
|  |  |  | Baseline Dataset Freeze & Data Readiness Sign-Off | > Freeze the training and validation dataset for offline development > Joint sign-off that the data is fit for modelling > Record known data limitations carried into the PoC | TRUE | TRUE | FALSE | 2026-09-15 | 2026-09-17 |  |  |  | Not Started |  |  | Data readiness sign-off
2 | M2 | Model Development | Offline Model Development | ML Model Development - Kiln Golden Batch | > Define the golden batch reference envelope from best-performing historical runs > Model deviation of kiln operation against the golden envelope > Generate setpoint guidance for stable, low-variability kiln operation | TRUE | FALSE | FALSE | 2026-09-18 | 2026-10-23 |  |  |  | Not Started |  |  | Kiln Golden Batch model (offline)
|  |  |  | ML Model Development - C3S Soft Sensor | > Build a predictive model for C3S from kiln and raw mix process parameters > Train and tune on the frozen historical dataset > Predict C3S continuously between lab sampling intervals | TRUE | FALSE | FALSE | 2026-09-18 | 2026-10-23 |  |  |  | Not Started |  |  | C3S soft sensor model (offline)
|  |  |  | ML Model Development - Free Lime Soft Sensor | > Build a predictive model for Free Lime from kiln thermal and process parameters > Train and tune on the frozen historical dataset > Predict Free Lime continuously between lab sampling intervals | TRUE | FALSE | FALSE | 2026-09-18 | 2026-10-23 |  |  |  | Not Started |  |  | Free Lime soft sensor model (offline)
|  |  | Offline Validation | Back-Testing on Hold-Out Historical Period | > Validate all three models on a hold-out period not used in training > Report accuracy per model against actual lab results > Document failure modes and operating regimes with weak data coverage | TRUE | FALSE | FALSE | 2026-10-12 | 2026-10-23 |  |  |  | Not Started |  |  | Offline back-testing results
|  |  |  | Offline Model Review with Adani Process Team | > Walkthrough of model logic and back-testing results > Capture process-team feedback on physical plausibility of the drivers > Confirm readiness to enter shadow testing | TRUE | TRUE | FALSE | 2026-10-20 | 2026-10-23 |  |  |  | Not Started |  |  | Offline model review record
|  | Live Data Integration | Live Data Pipeline Setup | Live Data Interface Design & Agreement | > Agree push mechanism, schema, frequency and latency for the live feed > Confirm security, network and access requirements > No hardware in scope - software integration only | TRUE | TRUE | TRUE | 2026-09-18 | 2026-09-25 |  |  |  | Not Started |  |  | Live data interface specification
|  |  |  | Live Data Feed Setup by Adani / AWS | > Adani Cement and AWS to stand up the live data push to Faclon > Provision credentials, endpoints and network access > Confirm live tag coverage matches the historical dataset | FALSE | TRUE | TRUE | 2026-09-28 | 2026-10-16 |  |  |  | Not Started |  | Dependency: 1. Owned by Adani Cement and AWS 2. Shadow testing cannot start until this feed is live and stable
|  |  |  | Live Feed Ingestion & Validation at Faclon | > Ingest the live feed onto IOsense and validate against DCS / HMI values > Check timestamp alignment, engineering units and update frequency > Confirm feed stability over a continuous run | TRUE | TRUE | TRUE | 2026-10-12 | 2026-10-23 |  |  |  | Not Started |  |  | Validated live data feed on IOsense
|  | Application Development | Operator Dashboard Build | IOsense Application Development - Golden Batch & Soft Sensor Views | > Build the operator dashboard for kiln golden batch deviation > Build C3S and Free Lime soft sensor prediction views > Prediction vs lab actual comparison view for the shadow period | TRUE | FALSE | FALSE | 2026-09-28 | 2026-10-23 |  |  |  | Not Started |  |  | Operator dashboard on IOsense
|  |  |  | Model - Application Integration | > Wire the three models into the application for scheduled inference > Configure refresh frequency, prediction horizon and trend retention | TRUE | FALSE | FALSE | 2026-10-12 | 2026-10-23 |  |  |  | Not Started
|  |  |  | Application Walkthrough with Adani Users | > Demonstrate the dashboard to plant, process and quality users on replayed data > Capture change requests before shadow go-live | TRUE | TRUE | FALSE | 2026-10-20 | 2026-10-23 |  |  |  | Not Started |  |  | Application walkthrough and change request log
3 | M3 | Shadow Testing on Live Data | Shadow Run | Shadow Mode Go-Live | > All three models switched to run on the live data feed > Predictions logged and displayed in advisory mode only - no control action > Start of the four-week shadow window | TRUE | TRUE | TRUE | 2026-10-26 | 2026-10-26 |  |  |  | Not Started |  |  | Models running live in shadow mode
|  |  |  | Prediction vs Lab Result Reconciliation | > Compare C3S and Free Lime predictions against every lab sample > Track running accuracy across the shadow window > Log every deviation with its process context | TRUE | TRUE | FALSE | 2026-10-26 | 2026-11-20 |  |  |  | Not Started |  |  | Weekly shadow performance log
|  |  |  | Golden Batch Deviation Tracking | > Track kiln deviation against the golden envelope in live operation > Review flagged deviations with the kiln control room > Record operator response and usefulness of the guidance | TRUE | TRUE | FALSE | 2026-10-26 | 2026-11-20 |  |  |  | Not Started
|  |  |  | Model Drift Monitoring & In-Flight Tuning | > Monitor drift between offline and live performance > Retune models against observed live behaviour where required > Version and document every model change made during shadow | TRUE | FALSE | FALSE | 2026-10-26 | 2026-11-20 |  |  |  | Not Started
|  |  | Shadow Review | Shadow Review - Checkpoint 1 | > Two-week checkpoint on live accuracy and operator feedback > Agree corrective actions for the remaining shadow period | TRUE | TRUE | FALSE | 2026-11-09 | 2026-11-09 |  |  |  | Not Started |  |  | Checkpoint 1 review record
|  |  |  | Shadow Review - Checkpoint 2 | > Closing review of the shadow window > Freeze model versions for PoC evaluation | TRUE | TRUE | FALSE | 2026-11-20 | 2026-11-20 |  |  |  | Not Started |  |  | Checkpoint 2 review record and frozen model versions
4 | M4 | PoC Closure | Evaluation & Handover | PoC Performance Evaluation | > Consolidate offline and shadow results for all three models > Evaluate against the success criteria agreed at kick-off > Quantify observed benefit and projected benefit at scale | TRUE | TRUE | FALSE | 2026-11-23 | 2026-11-24 |  |  |  | Not Started |  |  | PoC evaluation summary
|  |  |  | PoC Report Submission | > Submit the PoC report covering approach, results, limitations and lessons > Include the data and integration dependencies observed during the PoC | TRUE | FALSE | FALSE | 2026-11-24 | 2026-11-25 |  |  |  | Not Started |  |  | PoC report
|  |  |  | Go / No-Go Review & Scale-Up Recommendation | > Joint go / no-go decision with Adani Cement and AWS > Recommendation on scale-up scope, additional kilns / lines and productionisation > Closes the 90-day PoC window (Day 1 = 28 Aug 2026) | TRUE | TRUE | TRUE | 2026-11-26 | 2026-11-26 |  |  |  | Not Started |  |  | Go / No-Go decision and scale-up recommendation