## Timeline
SN | Milestone | Step | Main Task | Sub Task | Details | Faclon | HZL Business | HZL Digital | V Spark | Start Date | Target Date | Revised Target Date | Actual Start Date | Actual End Date | Status | Faclon Remarks for Delay | Remarks | Handoffs to HZL
1 | M1 | Application Design & Project Kickoff | Project Initiation | Project Kick-Off Meeting | > On-site meeting at Zawar Mines with HZL and Faclon teams | TRUE | TRUE | TRUE | TRUE | 2026-04-13 | 2026-04-13 |  | 2026-04-13 | 2026-04-13 | Completed
|  |  |  | Pre Installation Site visit/ data readiness assesment | > Access energy meter and all data gathering, OSI PI system readiness, coal data entry readiness > HR complince, vendor and third-party onboarding > Power and Ethernet cabling, cable termination, OFC cabling > Planned shutdown coordination | TRUE | TRUE | TRUE | FALSE | 2026-04-21 | 2026-04-23 |  | 2026-04-21 | 2026-04-23 | Completed
|  |  | Pre-Commissioning Tasks | Application prototype | > APC reduction application > Coal data entry application | TRUE | FALSE | FALSE | FALSE | 2026-04-27 | 2026-05-04 |  | 2026-04-27 | 2026-05-04 | Completed |  | Dependencies: 1. Faclon - Share filtererd list of tags to Swapnil for verification of data between DCS and Pi Server - Resolved | Application Prototype for APC and Quality Data Ingestion
|  | DCS Data Integration | Live and Historical Data Integration | Live Data Integration - Existing DCS | > Setup and Deploy Data Connector for Pi Server | TRUE | FALSE | FALSE | TRUE | 2026-04-27 | 2026-05-04 | 2026-05-18 | 14/05/2026 | 2026-06-01 | Completed | > We received the tag list on 30th May only. | Dependency: 1. HZL - Get Tag Mapping for DCS Tag to Pi Parameter Mapping 2. Documentation update needed in Pi API Doc 3. 856 out of 1829 DCS Tags mapped currently Delay: 1. HZL yet to onboard tags in Pi API and share complete Parameter Mapping
|  |  |  | Historical Data Integration | > Import Historical Data for DCS Tags - 1 year at 1 min frequency | TRUE | TRUE | FALSE | FALSE | 2026-04-27 | 2026-05-04 | 2026-05-18 | 30/05/2026 | 2026-06-11 | Completed | > We received the API on 30th May only. Then there was a delay of 3-4 days at our end for integration. | Dependency: 1. HZL - Export excel or any other applicable format and share with Faclon 2. HZL - Energymeter data present in Historian at 15 minute interval 3. HZL - DCS Data for all 1829 tags for a period of 1 month - May 12 Delay: 1. HZL to export data out of Siemens system and share files
|  |  |  | Data Onboarding and Commissioning | > Creation of User Account > Setting up of Devices on I/O Foundry and I/O Sense | TRUE | FALSE | FALSE | FALSE | 2026-05-05 | 2026-05-07 | 2026-05-21 | 2026-06-01 | 2026-06-04 | Completed | > Data got integarted on June 1st only as we received the API on 30th May only. |  | I/O Sense User Account with DCS Data Onboarded
|  | Supply of Hardware | Hardware Procurement | Energy Meters & CTs Procurement Ethernet Pro Gateway Procurement IPC Gateway Procurement Cable & Conduit Procurement | > Procure 15x Schneider 6400 NG (Class 0.5) meters and 45x Split Core CTs (800/5A) > Procure 8x Ethernet Pro Gateways with panel enclosures, SMPS & accessories > Procure 1x IPC Gateway (i5 6th gen, 32GB RAM, 256GB SSD) and network switch. > Procure Modbus cable (500m), Ethernet LAN cable (150m), > Power cable, PVC conduit, PT & CT cables | TRUE | FALSE | FALSE | FALSE | 2026-04-27 | 2026-05-07 | 2026-05-12 | 2026-04-27 | 2026-05-16 | Completed | > IPC delivery got delayed from the OEM.
|  |  |  | Testing and dispatch | > Testing of all hardware line itmes and dispatch to the site | TRUE | FALSE | FALSE | FALSE | 2026-05-08 | 2026-05-15 | 2026-05-29 | 2026-05-16 | 2026-06-03 | Completed | > Partial material delay only - rest energy meters were sent on time. | Material Deliverd On 3 June | Quality Data Ingestion Application
2 | M2 | Installation and Commissioning | Field deployement | Hardware Installation | > Feeder Shutdown Coordination, > Energy Meter Installation (15 nos.),, > OPC UA Server Setup & Configuration, > IPC Gateway Installation, | TRUE | TRUE | TRUE | FALSE | 2026-05-20 | 2026-05-29 | 12/06/2026 20/07/2026 | 2026-06-03 | 20/07/2026 | Completed | > The original deployment was completed on 16 June. However, an additional requirement to install three more energy meters was identified at the end of the deployment. This required another site visit, along with fabrication work for the installation. As this was an additional scope of work, the activity was delayed. | I & C activity completed
|  |  |  | Energymeter onboarding and commissioning | > All energy (existing and new) onboarding on the platform, > Energy meter commissioning with gateways | TRUE | TRUE | TRUE | FALSE | 2026-05-25 | 2026-05-30 | 2026-06-13 | 2026-07-15 | 20/07/2026 | Completed | > Delay due to additinal Instrument required (TV ,Mini PC & KeyBoard) And We Procured and Dispatch it on 6th July, Its a additional hardware which was not a part of PO | Parameters to be taken (Pi Tags acros 64 energymeters = 448): Voltage Current Power (all 3 types) Power Factor Forward Active Energy
|  |  |  | Data validation | > Data validation and testing for all onboarded devices, both manually and on the iOSense platform | TRUE | TRUE | FALSE | FALSE | 2026-06-01 | 2026-06-02 | 2026-06-16 | 2026-07-17 | 20/07/2026 | Completed | > Same reason as above. |  | I/O Sense User Account with Energymeter Data Onboarded
3 | M3 | Platform Setup, Application Customization and Configuration | Model Development | New Energy Meter Data Integration with PI System annd Connect to Faclon System from PI System | > Energy meter data integration with PI system over OPC and then from PI system to Faclon system over API | TRUE | FALSE | TRUE | FALSE | 30/05/2026 | 2026-06-25 | 15/08/2026 | 24/07/2026 | 2026-08-15 | Completed | > Work pending at HZL end - new energy meters to be integarted with PI. We have given our OPC connectivity for the integration. > 24th July we have setup the OPC connectivity for HZL PI system to integrate. |  | APC Application with Dynamic APC Benchmarking Module plugged in
|  |  |  | ML Model Development – Dynamic APC Benchmarking | > Develop model for APC benchmarking using historical and process data | TRUE | FALSE | FALSE | FALSE | 2026-05-08 | 2026-05-28 | 2026-06-11 | 2026-05-08 | 2026-06-11 | Completed | > We first did the manual analysis and then data was put in the application. |  | APC Application with Dynamic APC Benchmarking Module plugged in
|  |  |  | ML Model Development – RCA & Deviation Analysis | > Develop correlational analysis models for real-time root cause analysis of APC deviations | TRUE | FALSE | FALSE | FALSE | 2026-05-29 | 2026-06-29 | 13/07/2026 15/09/2026 |  |  | In Progress | > We have started working on analysis of the data for the model development; however, complete data is still awaited. Data from the new energy meters is yet to be integrated into the PI Server at the HZL end and subsequently synchronized with the Faclon system. |  | APC Application with RCA and Deviation Analysis Module plugged in
|  |  |  | ML Model Development – Process Optimization | > Develop optimization models to recommend set parameters for auxiliary consumption reduction | TRUE | FALSE | FALSE | FALSE | 2026-06-30 | 2026-07-30 | 13/08/2026 28/09/2026 |  |  | In Progress | > Same reason as above. |  | APC Application with Process Optimisation Module plugged in
|  |  | Application Developement | Application | > Application developement and integrating with the model | TRUE | FALSE | FALSE | FALSE | 30/07/2026 | 15/08/2026 | 2026-09-28 | 2026-06-11 |  | In Progress | > Final completion depends on Model development and model development right now awaiting the energy meters data.
|  |  |  | Alerts | > Alerts Configurations | TRUE | FALSE | FALSE | FALSE | 2026-06-22 | 2026-06-29 | 2026-10-07 |  |  | Not Started | > Final completion depends on Model development and model development right now awaiting the energy meters data. |  | Alerts configured as per required rules and relevant stakeholders mapped
|  |  |  | Reports | > Reports Configurations - APC Report, SCC Loss File Report, | TRUE | FALSE | FALSE | FALSE | 2026-06-22 | 2026-07-13 | 2026-10-07 | 2026-06-11 |  | In Progress | > Final completion depends on Model development and model development right now awaiting the energy meters data. |  | Reports configured/developed
|  | Training and Onboarding | User Training | Platform Training for Plant Users | > Train all stakeholders on I/O Sense platform navigation, dashboards and reports, reports AND alerts trainng > Train HZL team for optimization model interaction > Train on MIS report interpretation, alert management and escalation workflows | TRUE | TRUE | TRUE | TRUE | 2026-08-03 | 2026-08-17 | 2026-10-07 |  |  | Not Started
|  | Handover and Hypercare | Go Live | Go Live (80% Accuracy) | > Platform go-live with ML models at 80% recommendation accuracy | TRUE | TRUE | TRUE | TRUE | 2026-08-24 | 2026-08-24 | 2026-10-07 |  |  | Not Started
|  |  |  | UAT Sign-Off | > Formal UAT sign-off from HZL stakeholders | TRUE | TRUE | TRUE | TRUE | 2026-08-24 | 2026-09-07 | 2026-10-15 |  |  | Not Started
|  |  | Hypercare | Hypercare Support Activation | > Address all issues identified during go-live and fine-tune configurations | TRUE | TRUE | FALSE | TRUE | 2026-09-07 | -- |  |  |  | Not Started
|  |  |  | Model Retraining Plan | > Improve ML model accuracy from 80% to 95% with active HZL SME support | TRUE | TRUE | FALSE | FALSE | 2026-09-07 | -- |  |  |  | Not Started |  | Quarterly retraining cycles